SYNTHESIS OF DECISIONS

| Decision no. | Date | Subject of the decision | Status | Comments |
| --- | --- | --- | --- | --- |
| 1 | 25.03.2015 | Approving the Rules of Procedure of the Monitoring Committee for Interreg V-A Romania-Bulgaria Programme | Approved MC 1 25.03.2015 Belogradchik | n/a |
| 2 | 25.03.2015 | Approving the Communication Strategy for Interreg V-A Romania-Bulgaria Programme applicable to Priority axis 6 | Approved MC 1 25.03.2015 Belogradchik | n/a |
| 3 | 25.03.2015 | Approving the Applicant's Pack for the first call for proposals | Approved MC 1 25.03.2015 Belogradchik | n/a |
| 4 | 25.03.2015 | Approving the Methodology for using flat-rate for office and administrative costs for Interreg V-A Romania-Bulgaria Programme | Approved MC 1 25.03.2015 Belogradchik | n/a |
| 5 | 25.03.2015 | Approving the list of eligible expenditure for Interreg V-A Romania-Bulgaria Programme applicable to Priority axis 1-5 | Approved MC 1 25.03.2015 Belogradchik | http://www.interregrobg.eu/en/rules-of-implementation/programme-rules/list-of-eligible-expenditures-of-projects.html |
| 6 | 25.03.2015 | Approving the list of eligible expenditure for Interreg V-A Romania-Bulgaria Programme applicable to Priority axis 6 | Approved MC 1 25.03.2015 Belogradchik | n/a |
| 7 | 25.03.2015 | Approving the Multi-Annual Technical Assistance Strategy for Interreg V-A Romania-Bulgaria Programme | Approved MC 1 25.03.2015 Belogradchik | n/a |
| 8 | 15.05.2015 | Approving the Corrigendum to the Applicant's Pack for the first call of proposal of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | http://www.interregrobg.eu/en/calls-for-proposals/closed-calls.html |
| 9 | 02.06.2015 | Approving the Description of the Management and Control System for Interreg V-A Romania-Bulgaria Programme | Approved MC 2 06.06.2015 Balchik | n/a |
| 10 | 02.06.2015 | Approving the Visual Identity Manual for Interreg V-A Romania-Bulgaria Programme | Approved MC 2 06.06.2015 Balchik | n/a |
| 11 | 02.06.2015 | Approving the Anti-fraud Strategy for Interreg V-A Romania-Bulgaria Programme | Approved MC 2 06.06.2015 Balchik | n/a |
| 12 | 14.08.2015 | Approving the job descriptions for the staff of the Joint Secretariat for the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 13 | 02.10.2015 | Approving the "Project Manager - Technical Expert '' job description of the Joint Secretariat for Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 14 | 15.10.2015 | Approving the Applicant’s Pack for the Second Call for Proposals | Approved MC 3 15.10.2015 Bucharest | http://www.interregrobg.eu/en/calls-for-proposals/closed-calls.html |
| 15 | 15.10.2015 | Amending the list of eligible expenditure for Interreg V-A Romania-Bulgaria Programme applicable to Priority axis 1-5 and updating the Programme ceilings | Approved MC 3 15.10.2015 Bucharest | n/a |
| 16 | 15.10.2015 | Approving the List of approved and rejected projects submitted in the first call for proposals for the Interreg V-A Romania-Bulgaria Programme – June Deadline – soft projects | Approved MC 3 15.10.2015 Bucharest | http://interregrobg.eu/images/fisiere/programme-general/sod/Decision%2016.pdf |
| 17 | 15.10.2015 | Approving the Complaint Panel for soft projects – first call - Interreg V-A Romania-Bulgaria Programme | Approved MC 3 15.10.2015 Bucharest | n/a |
| 18 | 15.10.2015 | Not approving establishing an Info Point at Pleven | MC 3 15.10.2015 Bucharest | n/a |
| 19 | 15.10.2015 | Approving the Evaluation Plan for Interreg V-A Romania-Bulgaria Programme | Approved MC 3 15.10.2015 Bucharest | http://www.interregrobg.eu/images/fisiere/RO%20BG%20evaluation%20plan.pdf |
| 20 | 15.10.2015 | Approving using technical assistance funds from Interreg V-A Romania-Bulgaria Programme for closure of the Romania-Bulgaria Cross Border Cooperation Programme 2007-2013 | Approved MC 3 15.10.2015 Bucharest | n/a |
| 21 | 04.01.2016 | Approving the amendment of Decision no 16 of 15th of October 2015 | Approved Written procedure | n/a |
| 22 | 07.03.2016 | Approving the Corrigendum to the Applicant's Pack for the second call for proposals of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | http://www.interregrobg.eu/en/archive/110-revision-of-the-applicant-s-pack-for-the-second-call-for-proposals-deadline-15th-of-march-2016.html |
| 23 | 19.05.2016 | Approving the Annual Implementation Report for 2015 of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | http://www.interregrobg.eu/en/archive/138-the-annual-implementation-report-2015-submitted-to-the-european-commission.html |
| 24 | 19.05.2016 | Approving the List of the proposed modification of the ceilings expenditure of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 25 | 16.06.2016 | Approving the revision of The Description of the Management and Control System (DMSC) of Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 26 | 04.08.2016 | Approving the Annual Communication Plan for 2016 for Interreg V-A Romania-Bulgaria Programme | Approved MC 4 04.08.2016 Ruse | n/a |
| 27 | 04.08.2016 | Approving the amendment of Visual Identity Manual (VIM) for Interreg V-A Romania-Bulgaria Programme | Approved MC 4 04.08.2016 Ruse | http://www.interregrobg.eu/en/rules-of-implementation/programme-rules/visual-identity-manual.html |
| 28 | 04.08.2016 | Approving the next meeting of the Monitoring Committee | Approved MC 4 04.08.2016 Ruse | n/a |
| 29 | 04.08.2016 | Approving the revised version of the Description of the Management and Control System for Interreg V-A Romania-Bulgaria Programme | Approved MC 4 04.08.2016 Ruse | n/a |
| 30 | 14.11.2016 | Approving the List of approved and rejected projects submitted in the first call for proposals for the Interreg V-A Romania-Bulgaria Programme – September Deadline – hard projects | Approved Written procedure | http://interregrobg.eu/images/fisiere/programme-general/sod/Decision%2030.pdf |
| 31 | 14.11.2016 | Approving the Complaint Panel for hard projects – first call – Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 32 | 08.12.2016 | Approving the List of projects proposed for approval, rejection and re-evaluation, submitted in the second call for proposals for the Interreg V-A Romania-Bulgaria Programme – Deadline – 15th of March 2016. | Approved MC 6 08.12.2016 Pleven | http://interregrobg.eu/images/fisiere/programme-general/sod/Decision%2032.pdf |
| 33 | 08.12.2016 | Approving the Complaint Panel for the projects submitted under the second call for proposal, priority axes 4-5, Interreg V-A Romania-Bulgaria Programme. | Approved MC 6 08.12.2016 Pleven | n/a |
| 34 | 08.12.2016 | Approving the modification of the Rules of Procedure of the Monitoring Committee for Interreg V-A Romania-Bulgaria Programme | Approved MC 6 08.12.2016 Pleven | n/a |
| 35 | 30.03.2017 | Approving the Applicant’s Pack for the Third Call for Proposals | Approved MC 7 30.03.2017 Calarasi | http://www.interregrobg.eu/en/calls-for-proposals/open-calls.html |
| 36 | 30.03.2017 | Approving the changes of the Application Form for the project no. 16.4.2.067, e-MS code ROBG - 186, selected for funding under Interreg V-A Ro-Bg Programme, second call for proposals, in the pre-contracting period. | Approved MC 7 30.03.2017 Calarasi | n/a |
| 37 | 30.03.2017 | Approving the budget reductions in the pre-contracting period for the project no. 16.5.2.010, e-MS code ROBG – 136, selected for funding under Interreg V-A Ro-Bg Programme, second call for proposals. | Approved MC 7 30.03.2017 Calarasi | n/a |
| 38 | 30.03.2017 | Approving the modification of the Application Form in the pre-contracting period for the project no. 16.5.2.003, e-MS code ROBG – 188, selected for funding under Interreg V-A Ro-Bg Programme, second call for proposals. | Approved MC 7 30.03.2017 Calarasi | n/a |
| 39 | 30.03.2017 | Approving the budget reductions in the pre-contracting period for the project no. 16.4.2.077, e-MS code ROBG – 144, selected for funding under Interreg V-A Ro-Bg Programme, second call for proposals. | Approved MC 7 30.03.2017 Calarasi | n/a |
| 40 | 30.03.2017 | Approving the budget reductions in the pre-contracting period for the project no. 16.4.2.026, e-MS code ROBG – 158, selected for funding under Interreg V-A Ro-Bg Programme, second call for proposals. | Approved MC 7 30.03.2017 Calarasi | n/a |
| 41 | 30.03.2017 | Approving the amendment of Decision no 30 of 14th of November 2016- approving the List of approved and rejected projects submitted in the first call for proposals for the Interreg V-A Romania-Bulgaria Programme – October deadline – hard projects. | Approved MC 7 30.03.2017 Calarasi | n/a |
| 42 | 30.03.2017 | Approving the amendment of Decision no 32 of 08th of December 2016- approving the List of approved and rejected projects submitted in the second call for proposals for the Interreg V-A Romania-Bulgaria Programme – deadline for projects 15th of March 2016. | Approved MC 7 30.03.2017 Calarasi | n/a |
| 43 | 30.03.2017 | Approving on the projects in the reserve list for PAs 1, 2 and 3, to use of financial allocation for these projects, with scores above 65 (15.2.1.077, 15.2.1.036, 15.2.1.046) | Approved MC 7 30.03.2017 Calarasi | n/a |
| 44 | 30.03.2017 | Approving the list of rejected projects submitted under the second call for proposals, reevaluated according to the MC decision 32/08.12.2016 | Approved MC 7 30.03.2017 Calarasi | n/a |
| 45 | 30.03.2017 | Approving the revised job descriptions for the staff of the Joint Secretariat for the Interreg V-A Romania-Bulgaria Programme | Approved MC 7 30.03.2017 Calarasi | n/a |
| 46 | 02.05.2017 | Approving the changes of the Application Form for the project no. 16.4.2.076 / ROBG-151, selected for funding under Interreg V-A Ro-Bg Programme, second call for proposals, in the pre-contracting periode | Approved Written procedure | http://www.interregrobg.eu/en/calls-for-proposals/closed-calls.html |
| 47 | 11.05.2017 | Approving the amendment of Decision no. 42 of 30th of March 2017 | Approved Written procedure | n/a |
| 48 | 23.06.2017 | Approving the Annual Implementation Report 2016. | Approved MC 8 23.06.2017 Craiova | http://www.interregrobg.eu/en/248-on-25th-of-july-2017-the-annual-implementation-report-2016-of-interreg-v-a-romania-bulgaria-was-acceptable-by-the-european-commission.html |
| 49 | 02.08.2017 | Approving the List of expressions of interest approved for step 2 and the List of expressions of interest rejected for the third call for proposals for the Interreg V-A Romania-Bulgaria Programme – Deadline – 15th of May 2017 | Approved MC 9 02.08.2017 Bucharest | http://www.interregrobg.eu/images/fisiere/calls/Applicants%20guide%20call%203%20step%202/Annex%201%20-%20List%20of%20EoI%20approved%20for%20step%202%20new%20doc.pdf |
| 50 | 02.08.2017 | Approving the Revised Applicant’s Pack for the Third Call for Proposals | Approved MC 9 02.08.2017 Bucharest | http://www.interregrobg.eu/ro/apeluri-de-proiecte/apeluri-deschise.html |
| 51 | 02.08.2017 | Approving the Complaint Panel for the EoIs and full applications submitted under the 3rd call for proposals, priority axes 1-3, Interreg V-A Romania-Bulgaria Programme, step 1 and 2 | Approved MC 9 02.08.2017 Bucharest | n/a |
| 52 | 02.08.2017 | Approving the rejection of the EoI ROBG 404, Acronym “BOGDA” submitted under the 3rd call for proposals, priority axis 3, Interreg V-A Romania-Bulgaria Programme, step 1 | Approved MC 9 02.08.2017 Bucharest | n/a |
| 53 | 11.10.2017 | Approving the changes of the Application form for the project 15.1.1.037, e-MS code: ROBG-138 submitted under the Interreg V-A Romania-Bulgaria Programme, first call for proposals | Approved Written procedure | n/a |
| 54 | 12.10.2017 | Approving the "List of rejected Expressions of Interest" related to the 4 EoIs (ROBG-378, ROBG-380, ROBG-388, ROBG-592) submitted under the third call for proposals for the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 55 | 13.10.2017 | Approving the extension of the submission deadline for full applications to be submitted under step 2 of the 3rd call for proposals, priority axes 1-3, Interreg V-A Romania-Bulgaria Programme until 23.10.2017, 16.00 o'clock. | Approved Written procedure | n/a |
| 56 | 25.10.2017 | Approving the changes from the pre-contracting phase for the project 15.3.1.040, e-MS code: ROBG-195, submitted under the first call for proposals, hard projects for the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 57 | 30.10.2017 | Approving the modification of the Description of the Management and Control System for Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 58 | 02.11.2017 | Approving the changes in the project partnership for the project no. 16.5.2.017 / e-MS code ROBG-168, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 59 | 07.11.2017 | Approving the changes in the project partnership for the project no. 16.4.2.036 / e-MS code ROBG-161, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 60 | 15.11.2017 | Approving the changes in the project partnership for the project no. 16.4.2.104 / e-MS code ROBG-192, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 61 | 24.11.2017 | Approving the changes in the project partnership for the project no. 15.3.1.017 / e-MS code ROBG-23, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 62 | 28.12.2017 | Approving the modification of the description of the management and control system for Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 63 | 28.12.2017 | Approving the selection for financing of two applications which have received scores higher than 85 points in the evaluation process, namely eMS code 528 and 441, third call for proposals for the Interreg V-A Romania-Bulgaria Programme – 2nd step - Deadline – 23rd of October 2017 | Approved Written procedure | n/a |
| 64 | 28.12.2017 | Approving the extension of implementation periods over the maximum limits foreseen in the Applicant’s Guides for projects financed under INTERREG V-A Romania-Bulgaria Programme 2014-2020 | Approved Written procedure | n/a |
| 65 | 10.01.2018 | Approving the revised List of ceilings of the INTERREG V-A Romania-Bulgaria Programme 2014-2020 | Approved Written procedure | n/a |
| 66 | 18.01.2018 | Approving the selection for financing of two applications which have received scores higher than 85 points in the evaluation process, namely eMS code 408 and 351, third call for proposals for the Interreg V-A Romania-Bulgaria Programme – 2nd step - Deadline – 23rd of October 2017 | Approved Written procedure | n/a |
| 67 | 18.01.2018 | Approving the extension of the implementation period of the project no. 15.2.1.065 / e-MS code ROBG-15, in implementation under Interreg V-A Romania-Bulgaria Programme, until 02.08.2017 | Approved Written procedure | n/a |
| 68 | 25.01.2018 | Approving the changes from the pre-contracting phase for the project 16.4.2.046, e-MS code: ROBG-175, submitted under the second call for proposals for the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 69 | 26.01.2018 | Approving the extension of the implementation period of the project no. 15.2.1.052 / e-MS code ROBG-10, in implementation under Interreg V-A Romania-Bulgaria Programme, until 18.07.2017 | Approved Written procedure | n/a |
| 70 | 31.01.2018 | Approving the selection for financing of two applications which have received scores higher than 85 points in the evaluation process, namely eMS code 439 and 432, third call for proposals for the Interreg V-A Romania-Bulgaria Programme – 2nd step - Deadline – 23rd of October 2017 | Approved Written procedure | n/a |
| 71 | 12.02.2018 | Approving the changes in the project partnership for the project no. 16.5.2.010 / e-MS code ROBG-136, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 72 | 22.03.2018 | Approval of the List of approved and rejected projects submitted under the third call for proposals for the Interreg V-A Romania-Bulgaria Programme – deadline – 23rd of October 2017 | Approved MC 10 22.03.2018 Veliko Tarnovo | n/a |
| 73 | 22.03.2018 | Approval of the revised Communication Strategy for Interreg V-A Romania-Bulgaria Programme | Approved MC 10 22.03.2018 Veliko Tarnovo | n/a |
| 74 | 22.03.2018 | Approval of the Annual Communication Plan for 2018 for Interreg V-A Romania-Bulgaria Programme | Approved MC 10 22.03.2018 Veliko Tarnovo | n/a |
| 75 | 13.04.2018 | Approving the List of Expressions of Interest approved for step 2 related to the 3 EoIs submitted under the third call for proposals for the Interreg V-A Romania-Bulgaria Programme - deadline - 15th of May 2017 for which the complaints were approved according to the Complaint's Panel decisions no. 36/14.11.2017, no. 37/14.11.2017 and no. 38/14.11.2017 | Approved Written procedure | n/a |
| 76 | 23.04.2018 | Approving the rejection of the financing for the project 15.2.1.098/e-MS code ROBG-154, selected under the first call for proposals - September deadline - hard projects | Approved Written procedure | n/a |
| 77 | 17.05.2018 | Approving the Annual Implementation Report for 2017 of the Interreg V-A Romania-Bulgaria Programme, which shall be submitted to the European Commission | Approved Written procedure | http://interregrobg.eu/en/programme/programme-targets-and-status.html |
| 78 | 22.05.2018 | Approving the changes in the project partnership for the project no. 16.4.2.100 / e-MS code ROBG-185, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 79 | 23.05.2018 | Approving the modifications made in Annex 9. Feasibility study to the Approved Application Form of the Lead Beneficiary - Negru Voda Local Council and in Annex 3. Application Form for the project 15.1.1.019/e-MS code ROBG-133, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 80 | 30.05.2018 | Approving the budget reductions in the pre-contracting period for the project ROBG-528, selected for funding under the Interreg V-A Romania-Bulgaria Programme, third call for proposals | Approved Written procedure | n/a |
| 81 | 31.05.2018 | Approving the extension of the implementation period of the project no. 16.5.2.014 / e-MS code ROBG-172, in implementation under Interreg V-A Romania-Bulgaria Programme, until 10.11.2019 | Approved Written procedure | n/a |
| 82 | 29.06.2018 | Approving the reporting method of the financial indicators included in the performance framework | Approved Written procedure | n/a |
| 83 | 16.07.2018 | Approving the selection for financing of project ROBG-422, submitted under the third call for proposals for the Interreg V-A Romania-Bulgaria Programme - deadline 23rd of October 2017 | Approved Written procedure | n/a |
| 84 | 06.08.2018 | Approving the treatment of project changes | Approved Written procedure | n/a |
| 85 | 29.08.2018 | Approving the selection for financing of project ROBG-378, submitted under the third call for proposals for the Interreg V-A Romania-Bulgaria Programme - deadline 9th of July 2018 | Approved Written procedure | n/a |
| 86 | 01.10.2018 | Approving the changes in the project partnership and extension of the implementation period of the project no. 16.4.2.056 / e-MS code ROBG-163, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 87 | 08.10.2018 | Approving the changes in the Annex 2 - Approved Application Form and A.9. Feasibility study/equivalent technical documents for the project no. 15.1.1.019 / e-MS code ROBG-133, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 88 | 12.10.2018 | Approving the overcontracting at Programme level, in priority axes 1 and 5, at a level of 15,61% above the financial allocation at Programme level | Approved Written procedure | n/a |
| 89 | 22.11.2018 | Approving the extension of the implementation period of the project e-MS code ROBG-128, in implementation under Interreg V-A Romania-Bulgaria Programme, until 30.12.2020 | Approved Written procedure | n/a |
| 90 | 08.01.2019 | Approving the changes in the pre-contracting phase for the project e-MS code: ROBG-415, submitted under the third call for proposals for the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 91 | 01.02.2019 | Approving the rejection of the financing for the project e-MS code ROBG-585, selected under the third call for proposals - deadline 23rd of October 2017 | Approved Written procedure | n/a |
| 92 | 27.02.2019 | Approving the rejection of financing for project e-MS code ROBG-593, selected under the third call for proposals - deadline 23rd of October 2017 | Approved Written procedure | n/a |
| 93 | 27.02.2019 | Approving the rejection of financing for project e-MS code ROBG-372, selected under the third call for proposals - deadline 23rd of October 2017 | Approved Written procedure | n/a |
| 94 | 27.02.2019 | Approving the changes in the pre-contracting phase for the project e-MS code: ROBG-259, submitted under the second call for proposals for the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 95 | 27.02.2019 | Approving the Annual Communication Plan for 2019 for Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 96 | 28.03.2019 | Approving the extension of the implementation period of the project e-MS code ROBG-160, in implementation under Interreg V-A Romania-Bulgaria Programme, until 20.07.2019 | Approved Written procedure | n/a |
| 97 | 29.03.2019 | Approving the extension of the implementation period of the project e-MS code ROBG-139, in implementation under Interreg V-A Romania-Bulgaria Programme, until 03.11.2019 | Approved Written procedure | n/a |
| 98 | 16.04.2019 | Approving the modification of the Description of the Management and Control System for Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 99 | 10.05.2019 | Approving the changes in the project partnership for the project e-MS code ROBG-476, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 100 | 15.05.2019 | Approving the modification of the contribution (and quantification) to the Programme output indicator “Number of supported cross border mechanisms (agreements, networks, regulations, studies, policies, strategies, information exchange tools) to enhance cooperation capacity” of the project 16.5.2.010, e-MS code: ROBG-136, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 101 | 22.05.2019 | Approving the extension of the implementation period of the project e-MS code ROBG-135, in implementation under Interreg V-A Romania-Bulgaria Programme, until 29.03.2022 | Approved Written procedure | n/a |
| 102 | 29.05.2019 | Approving the modification of the contribution and quantification to the Programme output indicators related to Priority axis 4 of the project 16.4.2.052, e-MS code: ROBG-170, financed under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 103 | 30.05.2019 | Approving the extension of the implementation period of the project 15.1.1.037, e-MS code ROBG-138, in implementation under Interreg V-A Romania-Bulgaria Programme, until 11.07.2023 | Approved Written procedure | n/a |
| 104 | 04.06.2019 | Approving the extension of the implementation period of the project e-MS code ROBG-195, in implementation under Interreg V-A Romania-Bulgaria Programme, until 21.12.2021 | Approved Written procedure | n/a |
| 105 | 06.06.2019 | Approving the Methodology on establishing the application of financial corrections for not achieving or partial achieving the indicators within the financing contracts under the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 106 | 06.06.2019 | Approving the extension of the implementation period of the project 16.4.2.106, e-MS code ROBG-204, in implementation under Interreg V-A Romania-Bulgaria Programme, until 08.03.2020 | Approved Written procedure | n/a |
| 107 | 11.06.2019 | Approving the Annual Implementation Report for 2018 of the Interreg V-A Romania-Bulgaria Programme | Approved MC 11 11.06.2019 Varna | http://interregrobg.eu/images/fisiere/program/Implementation%20report_2014TC16RFCB021_2018_0_en.pdf |
| 108 | 11.06.2019 | Approving that Interreg V-A Romania-Bulgaria Programme will not use the Arachne system | Approved MC 11 11.06.2019 Varna | n/a |
| 109 | 11.06.2019 | Approving the Revised List of eligible expenditures for Interreg V-A Romania-Bulgaria Programme applicable to Priority Axis 6 – Technical Assistance | Approved MC 11 11.06.2019 Varna | n/a |
| 110 | 28.06.2019 | Approving the modification of the output indicators of the project "Combined efforts in support to disadvantaged people on the labour market in the cross-border area", project code: 16.4.2.056, e-MS code: ROBG-163, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 111 | 10.07.2019 | Approving the extension of the implementation period of the project e-MS code ROBG-160, in implementation under Interreg V-A Romania-Bulgaria Programme, until 20.11.2019 | Approved Written procedure | n/a |
| 112 | 17.07.2019 | Approving transfer of amounts between beneficiaries with impact on Bulgarian and Romanian State budgets allocation within the project “Investing in Road Safety and Improving the Connectivity of Ruse Municipality and Giurgiu County to TEN-T Transport Network”, e-MS code: ROBG-418, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 113 | 17.07.2019 | Approving the rejection of financing for project e-MS code ROBG-574, selected under the third call for proposals - deadline 23rd of October 2017 | Approved Written procedure | n/a |
| 114 | 19.07.2019 | Approving the changes in the project partnership for the project ROBG-271, “Tutrakan – Oltenita an Innovative Cultural Bridge for Sustainable Regional Development”, in implementation under Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 115 | 24.07.2019 | Approving the extension of the implementation period of the project e-MS code ROBG-175, in implementation under Interreg V-A Romania-Bulgaria Programme, until 16.10.2020 | Approved Written procedure | n/a |
| 116 | 25.07.2019 | Approving the extension of the implementation period of the project e-MS code ROBG-150, in implementation under Interreg V-A Romania-Bulgaria Programme, until 22.11.2019 | Approved Written procedure | n/a |
| 117 | 31.07.2019 | Approving the extension of the implementation period of the project e-MS code ROBG-188, in implementation under Interreg V-A Romania-Bulgaria Programme, until 11.05.2020 | Approved Written procedure | n/a |
| 118 | 13.08.2019 | Approving the changes in the pre-contracting phase of project ROBG - 383, “Better connected secondary and tertiary nodes to TEN-T core and comprehensive network through joint CBC measures” | Approved Written procedure | n/a |
| 119 | 05.09.2019 | Approving the extension of the implementation period of the project e-MS code ROBG-132, in implementation under Interreg V-A Romania-Bulgaria Programme, until 31.12.2020 | Approved Written procedure | n/a |
| 120 | 10.09.2019 | Approving the changes in the Technical Project for the investment objective Road DOB-3032 (II-29 Dobrich – General Toshevo) - Dabovik from km 0+000 to km 4+500 of Beneficiary 2: General Toshevo Municipality and reduction of the target value set for the output indicator “Total length of reconstructed or upgraded roads”, project e-MS code: ROBG-133 in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 121 | 18.10.2019 | Approving the modification of the description of the project contribution to the result indicator “Population that have access to joint employment initiatives” and the extension of the implementation period of the project e-MS code: ROBG-183, in implementation under Interreg V-A Romania-Bulgaria Programme, until 30.04.2020 | Approved Written procedure | n/a |
| 122 | 24.10.2019 | Approving the extension of the implementation period of the project e-MS code: ROBG-139, in implementation under Interreg V-A Romania-Bulgaria Programme, until 03.04.2021 | Approved Written procedure | n/a |
| 123 | 24.10.2019 | Approving the extension of the implementation period of the project e-MS code: ROBG-130, in implementation under Interreg V-A Ro-Bg Programme, until 11.11.2020 | Approved Written procedure | n/a |
| 124 | 28.10.2019 | Approving the changes in the approved technical documentations, project e-MS code: ROBG-138 in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 125 | 07.11.2019 | Approving the rejection of financing for project e-MS code ROBG-250, selected under the second call for proposals, soft project | Approved Written procedure | n/a |
| 126 | 11.11.2019 | Approving the reallocation of amount between budget chapters of the Lead Beneficiary and extension of the implementation period of the project e-MS code: ROBG-127, in implementation under Interreg V-A Ro-Bg Programme, until 30.08.2020 | Approved Written procedure | n/a |
| 127 | 27.11.2019 | Approving the extension of the implementation period of the project e-MS code: ROBG-476, in implementation under Interreg V-A Ro-Bg Programme, until 06.06.2020 | Approved Written procedure | n/a |
| 128 | 29.11.2019 | Approving measures necessary for the accurate reporting of projects contribution to the Programme indicators values when reporting to the European Commission | Approved Written procedure | n/a |
| 129 | 05.12.2019 | Approving the extension of the implementation period of the project e-MS code: ROBG-399, in implementation under Interreg V-A Ro-Bg Programme, until 30.06.2020 | Approved Written procedure | n/a |
| 130 | 10.12.2019 | Approving the extension of the implementation period of the project e-MS code: ROBG-195, in implementation under Interreg V-A Ro-Bg Programme, until 21.02.2023 | Approved Written procedure | n/a |
| 131 | 11.12.2019 | Approving the exception from the 4+ rule for the projects ROBG-427 and ROBG-409, selected under Interreg V-A Ro-Bg Programme, the third call for proposals | Approved Written procedure | n/a |
| 132 | 12.12.2019 | Approving the extension of the implementation period of the project e-MS code: ROBG-507, in implementation under Interreg V-A Ro-Bg Programme, until 28.06.2020 | Approved Written procedure | n/a |
| 133 | 16.01.2020 | Approving the Annual Communication Plan 2020 for the Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 134 | 28.01.2020 | Approving the extension of the implementation period of the project e-MS code: ROBG-442 until 21.12.2023 and modification of the output indicator “Number of joint mechanisms (e.g. route guidance, incidents/emergencies detection and management, studies on traffic flows, feasibility studies addressing cross-border transport issues, traffic safety measures, black-spot maps, awareness raising activities); to facilitate the connection of secondary/tertiary nodes to TEN-T infrastructure”, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 135 | 28.01.2020 | Approving the extension of the implementation period of the project e-MS code: ROBG-366, in implementation under Interreg V-A Ro-Bg Programme, until 31.05.2020 | Approved Written procedure | n/a |
| 136 | 04.02.2020 | Approving accurate reporting of project RoBg-142, contribution to the Programme output indicators values when reporting to the European Commission | Approved Written procedure | n/a |
| 137 | 18.02.2020 | Approving the extension of the implementation period of the project e-MS code: ROBG-290, in implementation under Interreg V-A Ro-Bg Programme, until 08.10.2020 | Approved Written procedure | n/a |
| 138 | 24.02.2020 | Approving the modification of the List of Ceilings at the Interreg V-A Ro-Bg Programme level | Approved Written procedure | http://interregrobg.eu/en/rules-of-implementation/programme-rules/ceilings.html |
| 139 | 27.02.2020 | Approving the extension of the implementation period until 20.09.2020 and modification of Annex A.9 “Feasibility Study/equivalent technical documents”, project “Increasing accessibility to the TEN-T in the border area Negru – Voda - General Toshevo”, e-MS code: ROBG-133, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 140 | 05.03.2020 | Approving the extension of the implementation period of the project “Risk management and flood protection in cross-border regions Calarasi and Polski Trambesh”, e-MS code: ROBG – 137, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 141 | 16.03.2020 | Approving the extension of the implementation period of the project “Tutrakan-Calarasi an Innovative Cultural Bridge for Sustainable Regional Development”, project e-MS code: ROBG-271, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 142 | 16.03.2020 | Approving the reallocation of amount between the budget chapters of the Lead Beneficiary and extension of the implementation period of the project “Tradition and Dance – Bridge over the Danube”, e-MS code: ROBG-511, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 143 | 30.03.2020 | Approving the reallocation of amount between the budget chapters of the Lead Beneficiary - Belene Municipality and Beneficiary 2 - Calarasi Municipality and modifying the Application Form for project “Joint risk management for efficient reactions of the local authorities in the emergency situations”, e-MS code: ROBG-458, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 144 | 31.03.2020 | Approving the changes in the pre-contracting phase of project ROBG-409, “Preventing forest fire in Dolj and Lom, Montana cross border region”, selected for funding within the third call for proposals under the INTERREG V-A Romania-Bulgaria Programme 2014-2020 | Approved Written procedure | n/a |
| 145 | 21.04.2020 | Approving the extension of the implementation period of the project “Green management for protection of Nature park Rusenski Lom and Nature park Comana”, project e-MS code: ROBG-464, Lead Beneficiary – Directorate of Nature Park Rusenski Lom, until 07.01.2021, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 146 | 22.04.2020 | Approving the extension of the implementation period of the “Collective” Education”, project e-MS code: ROBG-188, Lead Beneficiary – Eurointegra Association, until 31.12.2020, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 147 | 23.04.2020 | Approving the mechanism to be put in place for using the potential economies by the projects under implementation within Interreg V-A Romania-Bulgaria Programme, dealing with risks and health related issues, in order to make acquisitions related to the fight against COVID-19 | Approved Written procedure | n/a |
| 148 | 30.04.2020 | Approving the extension of the implementation period of the project “A cross border union in the shadow of history”, project e-MS code: ROBG-134, Lead Beneficiary – Territorial Administrative Unit - Harsova Town, until 19.12.2021, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 149 | 30.04.2020 | Approving the extension of the implementation period of the project “Multi-cultural heritages and yachting on natural heritage Black Sea for a sustainable and creative tourism development on the cross border area Constanta Dobrich”, e-MS code: ROBG-366, Lead Beneficiary - Clopot Humanitarian Foundation, until 31.08.2020, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 150 | 05.05.2020 | Approving the extension of the implementation period of the project “Remember the war, appreciate your liberty”, project e-MS code: ROBG-449, Lead Beneficiary – Agency for Regional Development and Business Center - Vidin (ARDBC Vidin), until 31.10.2020, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 151 | 11.05.2020 | Approving the reallocation of amount between the budget chapters of the Lead Beneficiary and Beneficiary 2, extension of the implementation period until 30.04.2023 and technical changes occurred at the Technical Project stage in comparison with Feasibility Study for B2, project “Sustainable cross-border tourism products for Memorial Park “Grivitsa” and "Turnu" Fortress”, e-MS code: ROBG-397, Lead Beneficiary – Pleven Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 152 | 11.05.2020 | Approving the accurate reporting of project ROBG-186 contribution to the Programme output indicators values when reporting to the European Commission, implemented under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 153 | 14.05.2020 | Approving the reallocation of amounts between beneficiaries individual budgets (from B2 - Fire Safety and Civil Protection Directorate General – Ministry of Interior BG to the LB - Giurgiu County Council), transfer of amount between the budget chapters of the LB individual budget, reduction of the project budget, updating the LB feasibility study and modification of Section C.5 Work plan per work packages of Approved Application Form within the project “Investments for a safe region: Giurgiu County and Ruse District”, e-MS code: ROBG-135, Lead Beneficiary – Giurgiu County Council, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 154 | 21.05.2020 | Approving the extension of the implementation period of the project “Dragon boats”, e-MS code: ROBG-399, Lead Beneficiary: Agency for Regional Development and Business Center – Vidin (ARDBC Vidin), until 31.10.2020, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 155 | 02.06.2020 | Approving the extension of the implementation period of the project “Live, interactive and virtual environments for the museums of the lower Danube cross-border area between Romania and Bulgaria”, e-MS code: ROBG-499, Lead Beneficiary – University of Ruse Angel Kanchev, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 156 | 10.06.2020 | Approving accurate reporting of project RoBg-197, contribution to the Programme output indicators values when reporting to the European Commission | Approved Written procedure | n/a |
| 157 | 15.06.2020 | Approving the extension of the implementation period of the project “KIDS - An unique travelling concept in the RO-BG area for children and their families”, e-MS code: ROBG-507, Lead Beneficiary – Center of Consultancy and Project Management – EUROPROJECT, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 158 | 15.06.2020 | Approving the Annual Implementation Report for 2019 of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | https://interregrobg.eu/en/programme/programme-targets-and-status.html |
| 159 | 16.06.2020 | Approving the extension of the implementation period and technical changes occurred at the Technical Project stage in comparison with Feasibility Study for LB, project “The streamline of the traffic in the cross border Danubian area”, e-MS code: ROBG-138, Lead Beneficiary – Territorial Administrative Unit - Mehedinti County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 160 | 22.06.2020 | Approving accurate reporting of project RoBg-158, contribution to the Programme output indicators values when reporting to the European Commission | Approved Written procedure | n/a |
| 161 | 14.07.2020 | Approving the extension of the implementation period for the project “The Christian heritage along the cultural corridor Russe-Giurgiu”, e-MS code: ROBG-302, Lead Beneficiary - “Sveta Petka” Church - in implementation under Interreg V-A Ro-Bg Programme, reducing of the contribution to the output indicators, increasing of the total non-eligible expenditures, changing of the half implementation period, updating of the preliminary designs for the Lead Beneficiary and Beneficiary 3 by technical projects and changing of the Application Form | Approved Written procedure | n/a |
| 162 | 16.07.2020 | Approving the extension of the implementation period of the project “Co-ordinated and efficient reactions of the authorities in the emergency situations in Dolj-Vratsa region”, project e-MS code: ROBG – 195, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 163 | 10.08.2020 | Approving the extension of the implementation period of the project “Multi-cultural heritages and yachting on natural heritage Black Sea for a sustainable and creative tourism development on the cross border area Constanta Dobrich”, project e-MS code: ROBG – 366, Lead Beneficiary – Clopot Humanitarian Foundation, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 164 | 11.08.2020 | Approving the extension of the project implementation period and reallocation between budgetary chapters within the individual budget of Beneficiary 2, project “Streamlining the joint response actions to emergency situations”, project e-MS code: ROBG-351, Lead Beneficiary – General Inspectorate for Emergency Situations, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 165 | 11.08.2020 | Approving the extension of the implementation period of the project “Danube – A River with lot of common history”, project e-MS code: ROBG-476, Lead Beneficiary – “Open hand” Foundation, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 166 | 11.08.2020 | Approving the Interreg V-A Romania-Bulgaria Programme amendment | Approved Written procedure | n/a |
| 167 | 03.09.2020 | Approving the increasing of the total project non-eligible costs, modification of the project contribution to the output indicator ”Increase in expected number of visits to supported sites of cultural and natural heritage and attraction”, updating the technical and economical documentation of Beneficiary 2, revising section C2 “Project focus”, section C.2.4 “Non eligible expenditures” from Annex 1: Project Application for project e-MS code: ROBG-337, Lead Beneficiary – Cultural House “Razvitie-1869” - Vratsa, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 168 | 03.09.2020 | Approving the accurate reporting of project RoBg-187 contribution to the Programme output indicators values when reporting to the European Commission, implemented under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 169 | 15.09.2020 | Approving the accurate reporting of project RoBg-151 contribution to the Programme output indicators values when reporting to the European Commission, implemented under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 170 | 17.09.2020 | Approving the accurate reporting of project RoBg-578 contribution to the Programme output indicators values when reporting to the European Commission, implemented under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 171 | 25.09.2020 | Approving the extension of the implementation period and modifications within the description of the project activities and the budget of the project “Improving safety of navigability on Danube river in the Calarasi – Silistra cross – border region”, e-MS code: ROBG-478, Lead Beneficiary – Territorial Administrative Unit – Calarasi County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 172 | 28.09.2020 | Approving the amendment of the Anti-fraud Strategy for Interreg V-A Romania - Bulgaria Programme | Approved Written procedure | n/a |
| 173 | 29.09.2020 | Approving the extension of the implementation period and correction of the project title in eMS of the project “The Written Treasures of Lower Danube”, e-MS code: ROBG-290, Lead Beneficiary - Global Libraries Bulgaria Foundation, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 174 | 01.10.2020 | Approving the extension of the implementation period and the extension of the half of the implementation period of the project “Creating an innovative and integrated cross-border tourist product between "Vrachanski Balkan" and "Iron Gate" natural parks”, e-MS code: ROBG-378, Lead Beneficiary - Administration of Natural park "Vrachanski Balkan", in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 175 | 05.10.2020 | Approving the extension of the implementation period of the project “Silistra- Ecofriendly- Viable- Electrical- Navodari Transport”, e-MS code: ROBG-432, Lead Beneficiary - Territorial Administrative Unit – Navodari Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 176 | 08.10.2020 | Approving the extension of the implementation period and the modifications within the approved application form related to the extension of the implementation period for the project “Stimulation and increase of the employment and cross-border mobility in the cross-border region - 16.4.2.046”, e-MS code: ROBG-175, Lead Beneficiary – Belene Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 177 | 12.10.2020 | Approving the extension of the implementation period, modifications within the description of the project activities and related to the Application Form of the project “Developing common tourism products and rehabilitation of cultural heritage”, e-MS code: ROBG-491, Lead Beneficiary – Municipality of Silistra, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 178 | 15.10.2020 | Approving the extension of the implementation period of the project “Improvement of the transport safety in the common Bulgarian-Romanian stretch of the Danube river through development of the emergency response by cross-border cooperation”, e-MS code: ROBG-522, Lead Beneficiary - Executive Agency "Maritime Administration", in implementation under Interreg VA Ro-Bg Programme | Approved Written procedure | n/a |
| 179 | 20.10.2020 | Approving the revised List of ceilings of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | https://interregrobg.eu/en/rules-of-implementation/programme-rules/ceilings.html |
| 180 | 05.11.2020 | Approving the extension of the implementation period and modifications within the budget of the project “Development of the River Danube for better connectivity of the Euroregion Ruse-Giurgiu with Pan-European transport corridor №7”, e-MS code: ROBG-130, Lead Beneficiary – Ruse Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 181 | 09.11.2020 | Approving the extension of the implementation period for the project “Improved coordination and Social policies between Municipality of Byala and commune Gradinari for Effective cross-border region”, e-MS code: ROBG-278, Lead Beneficiary - Municipality of Byala - in implementation under Interreg V-A Ro-Bg Programme, modification of the contribution to the output indicators, extension of the project implantation period and changing of the Application Form | Approved Written procedure | n/a |
| 182 | 12.11.2020 | Approving the extension of the implementation period of the project “Multi-cultural heritages and yachting on natural heritage Black Sea for a sustainable and creative tourism development on the cross border area Constanta Dobrich”, e-MS code: ROBG-366, Lead Beneficiary – Clopot Humanitarian Foundation, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 183 | 16.11.2020 | Approving accurate reporting of project RoBg-356, contribution to the Programme output indicators values when reporting to the European Commission | Approved Written procedure | n/a |
| 184 | 26.11.2020 | Approving the replacement of the former Annex AF2 Preliminary Design on behalf of the Lead Beneficiary by the new developed Technical Design, replacement of the Annex AF2 Preliminary Design on behalf of Beneficiary 2 by the new developed Technical Design and revision of Annex 1 – Project Application of the project “Improved nodes Giurgiu-Byala for a better connection to TEN-T infrastructure”, e-MS code ROBG-442, Lead Beneficiary - Territorial Administrative Unit – Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 185 | 03.12.2020 | Approving the extension of the implementation period of the project e-MS code: ROBG-132, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 186 | 04.12.2020 | Approving the extension of the implementation period and the modifications within the approved application form related with the extension of the implementation period for the project “Joint efforts against natural disasters”, e-MS code: ROBG-416, Lead Beneficiary – Mezdra Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 187 | 15.12.2020 | Approving the Annual Communication Plan for 2021 for Interreg V-A Romania-Bulgaria Programme | Approved MC 12 15.12.2020 Online meeting | n/a |
| 188 | 21.12.2020 | Approving the extension of the implementation period of the project “KIDS - An unique travelling concept in the RO-BG area for children and their families”, e-MS code: ROBG-507, Lead Beneficiary – Center of Consultancy and Project Management – EUROPROJECT, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 189 | 23.12.2020 | Approving the extension of the implementation period of the project “The Bridges of Time: An Integrated Approach for Improving the Sustainable Use of Nikopol-Turnu Magurele Cross-border Cultural Heritage”, e-MS code: ROBG-128, Lead Beneficiary – Nikopol Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 190 | 29.12.2020 | Approving the extension of the implementation period and technical changes occurred at the Technical Project stage in comparison with Preliminary design for LB of the project e-MS code: ROBG-568, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 191 | 14.01.2021 | Approving the extension of the implementation period of the project “Safety for our children”, e-MS code: ROBG-461, Lead Beneficiary – “Regional Development Agency and Business Center 2000”, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 192 | 08.02.2021 | Approving the extension of the implementation period of the project “Joint Investments in the field of emergency situation for Olt County Council and Dolna Mitropolia Municipality”, e-MS code: ROBG-244, Lead Beneficiary – Olt County Council, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 193 | 11.02.2021 | Approving the extension of the implementation period of the project “Children’s educational risk prevention crisis package C.A.R.E.”, e-MS code: ROBG-448, Lead Beneficiary – State Puppet Theatre Vidin, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 194 | 11.02.2021 | Approving the extension of the implementation period of the project “Multi-cultural heritages and yachting on natural heritage Black Sea for a sustainable and creative tourism development on the cross border area Constanta Dobrich”, e-MS code: ROBG-366, Lead Beneficiary – Clopot Humanitarian Foundation, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 195 | 17.02.2021 | Approving the extension of the implementation period of the project “Risk management and flood protection in cross-border regions Calarasi and Polski Trambesh”, project no. 15.3.1.041/ e-MS code: ROBG-137, Lead Beneficiary – Municipality of Polski Trambesh, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 196 | 17.02.2021 | Approving the extension of the implementation period of the project “Restoration of Unique Common Cultural Heritage And Promotion of Joint Tourism Product "Hamangia - First Civilisation of Old Europe”, e-MS code: ROBG-407, Lead Beneficiary – Shabla Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 197 | 22.02.2021 | Approving the extension of the implementation period of the project “Joint risk management and partnership in the border region Calarasi - Dobrich”, e-MS code: ROBG-415, Lead Beneficiary – Dobrichka Municipality, modification of Annex 5 - Overview of the equipment, services and works to be purchased by each beneficiary, of the Beneficiary 3 - Calarasi County Emergency Situations Inspectorate “Barbu Stirbei” and modification of the project contribution to the Programme output and result indicators, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 198 | 23.02.2021 | Approving the extension of the implementation period of the project “Live, interactive and virtual environments for the museums of the lower Danube cross-border area between Romania and Bulgaria”, e-MS code: ROBG-499, Lead Beneficiary – University of Ruse Angel Kanchev, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 199 | 24.02.2021 | Approving the extension of the implementation period of the project “Well-developed transportation system in the Euroregion Ruse-Giurgiu for better connectivity with TEN-T network”, e-MS code: ROBG-425, Lead Beneficiary – Territorial Administrative Unit – Giurgiu Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 200 | 01.03.2021 | Approving the extension of the implementation period of the project “Targeted efforts for improving road infrastructure in the cross border area”, e-MS code: ROBG-408, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 201 | 18.03.2021 | Approving the extension of the implementation period of the project “Borderless Health Through Sport and Cooperation – United in the Battle Against Diseases”, e-MS code: ROBG-139, Lead Beneficiary – Territorial Administrative Unit – Harsova Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 202 | 01.04.2021 | Approving the extension of the implementation period of the project “Increasing the efficiency of municipal health care in the border region Berkovitsa – Bailesti” - 16.5.2.019, e-MS code: ROBG-259, Lead Beneficiary – Municipality Berkovitsa, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 203 | 01.04.2021 | Approving the extension of the implementation period of the project “Sustainable cross-border tourism products for Memorial Park “Grivitsa” and "Turnu" Fortress”, e-MS code: ROBG-397, Lead Beneficiary – Pleven Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 204 | 09.04.2021 | Approving the extension of the implementation period of the project “Stimulation and increase of the employment and cross-border mobility in the cross-border region – 16.4.2.046”, e-MS code: ROBG-175, Lead Beneficiary – Belene Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 205 | 14.04.2021 | Approving the extension of the implementation period of the project “Improving the connection to the TEN-T network in the cross-border area Medgidia – Dobrich” e-MS code: ROBG-439, Lead Beneficiary – Territorial Administrative Unit - Medgidia Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 206 | 20.04.2021 | Approving the update of the Bill of quantities and values from the technical design of LB - Municipality of Varshets and 3 months of extension of the project implementation period (from 36 to 39 months), of the project “New destinations in cross-border tourism”, e-MS code: ROBG-471, Lead Beneficiary, Municipality of Varshets, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 207 | 20.04.2021 | Approving the replacement of the Annex AF2 – Feasibility studies/ equivalent technical documents (if the case) to the Project Application generated by the eMS, by Beneficiary 2 – Silistra Municipality with the Technical Design prepared during the project implementation; revision of the Section C.5 Work plan per workpackages, Section Project budget, part D. Project budget; Sections Project main output from the Application Form and project budget reduction with 0.01 euro for project e-MS code ROBG-432 “Silistra- Ecofriendly- Viable- Electrical- Navodari Transport”, Lead Beneficiary – Municipality of Navodari, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 208 | 10.05.2021 | Approving the extension of the implementation period of the project “Reconstruction and display of iconic cultural sites with high tourism potential in the Euroregion Ruse-Giurgiu” e-MS code: ROBG-424, Lead Beneficiary – Ruse Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 209 | 14.05.2021 | Approving the extension of the implementation period; revision of the project Application, generated by eMS (PART A - Project summary, A.1 Project identification; Project budget part D. Project budget; Section C.5 Work plan per workpackages; Section Project main output); project budget reduction with 0.02 euro and revision of Annex 4. Overview of the equipment, services and works to be purchased by the Lead Beneficiary for project “Tutrakan-Calarasi an Innovative Cultural Bridge for Sustainable Regional Development”, project e-MS code: ROBG-271, Lead Beneficiary – Historical Museum Tutrakan, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 210 | 20.05.2021 | Approving the Annual Implementation Report for 2020 of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 211 | 04.06.2021 | Approving the modification of the Description of Management and Control System for Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 212 | 04.06.2021 | Approving the extension of the implementation period of the project “The Written Treasures of Lower Danube” e-MS code: ROBG-290, Lead Beneficiary – Global Libraries Bulgaria Foundation, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 213 | 18.06.2021 | Approving the extension of the implementation period for the project “Dolj-Montana: Joint steps for a better connectivity”, project e-MS code: ROBG-375, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 214 | 24.06.2021 | Approving the extension of the implementation period of the project “KIDS - An unique travelling concept in the RO-BG area for children and their families” e-MS code: ROBG-507, Lead Beneficiary – CENTER OF CONSULTANCY AND PROJECT MANAGEMENT – EUROPROJECT, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 215 | 07.07.2021 | Approving the extension of the implementation period of the project “KIDS - An unique travelling concept in the RO-BG area for children and their families” e-MS code: ROBG-507, Lead Beneficiary – CENTER OF CONSULTANCY AND PROJECT MANAGEMENT – EUROPROJECT, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 216 | 16.07.2021 | Approving the extension of the implementation period of the project “I-TeN: Improved tertiary nodes Turnu Magurele - Nikopole for sustainable development of the region, for a better connection to TEN-T infrastructure” e-MS code: ROBG-132, Lead Beneficiary – Territorial Administrative Unit - Turnu Magurele Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 217 | 16.07.2021 | Approving the extension of the implementation period of the project “Culture Green”, e-MS code: ROBG-337, Lead Beneficiary – Cultural House “Razvitie-1869”- Vratsa, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 218 | 19.07.2021 | Approving the modification of the target value for the Project Result Indicator “PA 3 - R3.1 - The quality of the joint risk management in the CBC area” of the project “Partnerships for Overcoming the Disasters for a Safe Region”, e-MS code: ROBG-427, Lead Beneficiary – Territorial Administrative Unit Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 219 | 28.07.2021 | Approving the extension of the implementation period of the project “Improved coordination and Social policies between Municipality of Byala and commune Gradinari for Effective cross-border region” e-MS code: ROBG-278, Lead Beneficiary – Byala Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 220 | 02.08.2021 | Approving the extension of the implementation period of the project “Development of tourism potential, protection and promotion of the common heritage”, e-MS code: ROBG-453, Lead Beneficiary – General Toshevo Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 221 | 02.08.2021 | Approving the extension of the implementation period of the project “Investing in Road Safety and Improving the Connectivity of Ruse Municipality and Giurgiu County to TEN-T Transport Network”, e-MS code: ROBG-418, Lead Beneficiary – Ruse Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 222 | 06.08.2021 | Approving the extension of the implementation period of the project “Streamlining the joint response actions to emergency situations”, e-MS code: ROBG-351, Lead Beneficiary – General Inspectorate for Emergency Situations, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 223 | 19.08.2021 | Approving the modifications of the project “Better connection of Alexandria and Cherven Bryag to TEN-T”, e-MS code: ROBG-306, Lead Beneficiary – Territorial Administrative Unit – Alexandria Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 224 | 23.08.2021 | Approving the modifications made within the project “Culture in Eternity” e-MS code: ROBG-423, Lead Beneficiary – Elena Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 225 | 23.08.2021 | Approving the extension of the implementation period of the project “Joint efforts against natural disasters” e-MS code: ROBG-416, Lead Beneficiary – Mezdra Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 226 | 25.08.2021 | Approving the extension of the implementation period of the project “Efficient management in emergency situations in the cross-border region Calarasi-Veliko Tarnovo” e-MS code: ROBG-481, Lead Beneficiary – Territorial Administrative Unit – Calarasi County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 227 | 30.08.2021 | Approving the extension of the implementation period of the project “Joint Volunteering for a Safer Life” e-MS code: ROBG-332, Lead Beneficiary – Tutrakan Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 228 | 07.09.2021 | Approving the extension of the implementation period of the project “HÎRȘOVA-DOBRICHKA, TOGETHER ON THE BEAUTIFUL ROAD OF SUSTAINABLE DEVELOPMENT THROUGH CROSS BORDER CULTURE” e-MS code: ROBG-456, Lead Beneficiary – TAU Harsova Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 229 | 07.09.2021 | Approving the extension of the implementation period of the project “Tales of Culture, History and Nature” e-MS code: ROBG-413, Lead Beneficiary – TAU Videle Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 230 | 09.09.2021 | Approving the extension of the implementation period of the project “Joint Investments in the Field of Emergency Situations for Olt County Council and Dolna Mitropolia Municipality” e-MS code: ROBG-244, Lead Beneficiary – TAU Olt County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 231 | 13.09.2021 | Approving the extension of the implementation period of the project “Improvement of the transport safety in the common Bulgarian-Romanian stretch of the Danube river through development of the emergency response by cross-border cooperation” e-MS code: ROBG-522, Lead Beneficiary – Executive Agency "Maritime Administration", in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 232 | 24.09.2021 | Approving the extension of the implementation period of the project “A joint opened window to the universe mysteries” e-MS code: ROBG-528, Lead Beneficiary – Natural Science Museum Complex Constanta, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 233 | 28.09.2021 | Approving the extension of the implementation period of the project “Investments for a Safe Region: Giurgiu County and Ruse District – 15.3.1.023” e-MS code: ROBG-135, Lead Beneficiary – TAU Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 234 | 01.10.2021 | Approving the modifications of the project “Improving the connection to the TEN-T network in the cross-border area Medgidia - Dobrich” e-MS code: ROBG-439, Lead Beneficiary – TAU Medgidia Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 235 | 21.10.2021 | Approving the extension of the implementation period of the project “Development of tourism potential, protection and promotion of the common heritage”, e-MS code: ROBG-453, Lead Beneficiary – General Toshevo Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 236 | 03.11.2021 | Approving the extension of the implementation period of the project “Development of the River Danube for better connectivity of the Euroregion Ruse-Giurgiu with Pan-European transport corridor №7” e-MS code: ROBG-130, Lead Beneficiary – Ruse Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 237 | 18.11.2021 | Approving the extension of the implementation period of the project “I-TeN: Improved tertiary nodes Turnu Magurele - Nikopole for sustainable development of the region, for a better connection to TEN-T infrastructure” e-MS code: ROBG-132, Lead Beneficiary – Territorial Administrative Unit - Turnu Magurele Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 238 | 23.11.2021 | Approving the modifications for the project “New destinations in cross-border tourism”, e-MS code: ROBG-471, Lead Beneficiary – Varshets Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 239 | 03.12.2021 | Approving the extension of the project implementation period of the project “A Cross Border Union in the Shadow of History”, e-MS code: ROBG-134, Lead Beneficiary – TAU Harsova Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 240 | 07.12.2021 | Approving the extension of the implementation period of the project “Developing common tourism products and rehabilitation of cultural heritage” e-MS code: ROBG-491, Lead Beneficiary – Silistra Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 241 | 07.12.2021 | Approving the extension of the implementation period of the project “Joint efforts against natural disasters” e-MS code: ROBG-416, Lead Beneficiary – Mezdra Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 242 | 10.12.2021 | Approving the modifications for the project “The Bridges of Time: An Integrated Approach for Improving the Sustainable Use of Nikopol – Turnu Măgurele Cross-border Cultural Heritage”, e-MS code: ROBG-128, Lead Beneficiary – Municipality of Nikopol, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 243 | 16.12.2021 | Approving the Annual Communication Plan for 2022 for Interreg V-A Romania-Bulgaria Programme | Approved MC 13 16.12.2021 Online meeting | n/a |
| 244 | 16.12.2021 | Approving the usage of the technical assistance funds from Interreg V-A Romania-Bulgaria Programme for financing the preparation of PO 5.2 funded under Interreg VI-A Romania-Bulgaria Programme and for supporting the Strategy Board in developing the Integrated Territorial Strategy and for enhancing its capacity to implement and monitor the respective Integrated Territorial Strategy | Approved MC 13 16.12.2021 Online meeting | n/a |
| 245 | 16.12.2021 | Approving the extension of the implementation period of the project “Silistra- Ecofriendly- Viable- Electrical- Navodari Transport” e-MS code: ROBG-432, Lead Beneficiary – Territorial Administrative Unit - Navodari Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 246 | 05.01.2022 | Approving the extension of the implementation period of the project “Tutrakan-Calarasi an Innovative Cultural Bridge for Sustainable Regional Development” e-MS code: ROBG-271, Lead Beneficiary – Historical Museum Tutrakan, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 247 | 23.02.2022 | Approving the extension of the implementation period of the project “Risk management and flood protection in cross-border regions Calarasi and Polski Trambesh”, project no. 15.3.1.041/ e-MS code: ROBG-137, Lead Beneficiary – Municipality of Polski Trambesh, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 248 | 25.02.2022 | Approving the modifications for the project “Joint risk management and partnership in the border region Calarasi - Dobrich”, project e-MS code: ROBG-415, Lead Beneficiary – Dobrichka Municipality Administration, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 249 | 15.03.2022 | Approving the extension of the implementation period of the project “Stimulation and increase of the employment and cross-border mobility in the cross-border region”, e-MS code: ROBG-175, Lead Beneficiary – Belene Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 250 | 29.03.2022 | Approving the extension of the implementation period of the project “Improving the connection of tertiary nodes Mangalia and Balchik to TEN-T infrastructure”, e-MS code: ROBG-510, Lead Beneficiary – Territorial Administrative Unit - Mangalia Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 251 | 13.04.2022 | Approving the modifications for the project “I-TeN: Improved tertiary nodes Turnu Magurele - Nikopole for sustainable development of the region, for a better connection to TEN-T infrastructure” e-MS code: ROBG-132, Lead Beneficiary – Territorial Administrative Unit - Turnu Magurele Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 252 | 14.04.2022 | Approving the modifications for the project “Improved coordination and Social policies between Municipality of Byala and commune Gradinari for Effective cross-border region”, e-MS code: ROBG-278, Lead Beneficiary - Municipality of Byala - in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 253 | 15.04.2022 | Approving the extension of the implementation period of the project “Targeted efforts for improving road infrastructure in the cross border area”, e-MS code: ROBG-408, Lead Beneficiary – Territorial Administrative Unit – Dolj Couunty, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 254 | 15.04.2022 | Approving the extension of the implementation period of the project “Tradition and Dance – Bridge over the Danube” e-MS code: ROBG-511, Lead Beneficiary – Territorial Administrative Unit – Contesti Commune, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 255 | 19.04.2022 | Approving the modifications for the project “Tutrakan - Calarasi an Innovative Cultural Bridge for Sustainable Regional Development” e-MS code: ROBG-271, Lead Beneficiary – Historical Museum Tutrakan, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 256 | 29.04.2022 | Approving the extension of the implementation period of the project “Increasing the efficiency of municipal health care in the border region Berkovitsa – Bailesti”, e-MS code: ROBG-259, Lead Beneficiary – Berkovitsa Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 257 | 16.05.2022 | Approving the amendment of MC Decision no. 251 from 13.04.2022 | Approved Written procedure | n/a |
| 258 | 18.05.2022 | Approving the Annual Implementation Report for 2021 of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 259 | 06.06.2022 | Approving the modifications for the project “JOINT VOLUNTEERING FOR A SAFER LIFE” e-MS code: ROBG-332, Lead Beneficiary – Tutrakan Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 260 | 09.06.2022 | Approving the modifications for the project “Joint efforts against natural disasters” e-MS code: ROBG-416, Lead Beneficiary – Mezdra Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 261 | 23.06.2022 | Approving the modifications for the project “Developing common tourism products and rehabilitation of cultural heritage” e-MS code: ROBG-491, Lead Beneficiary – Municipality of Silistra, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 262 | 28.06.2022 | Approving the modifications for the project “Partnerships for Overcoming the Disasters for a safe region” e-MS code: ROBG-427, Lead Beneficiary – TAU Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 263 | 12.07.2022 | Approving the modifications for the project “Well connected nodes Giurgiu - Borovo to TEN-T transport network”, e-MS code: ROBG-440, Lead Beneficiary – Territorial Administrative - Unit Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 264 | 14.07.2022 | Approving the modifications for the project “Joint Investments in the Field of Emergency Situations for Olt County Council and Dolna Mitropolia Municipality” e-MS code: ROBG-244, Lead Beneficiary – Territorial Administrative Unit - Olt County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 265 | 20.07.2022 | Approving the extension of the implementation period of the project “Culture Green”, e-MS code: ROBG-337, Lead Beneficiary – Cultural House “Razvitie-1869”- Vratsa, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 266 | 01.08.2022 | Approving the modifications for the project “Montana – Dolj: Better access-closer communities (Acronym: MN-DJ: CLOSER)”, e-MS code: ROBG-390, Lead Beneficiary – Road Infrastructure Agency, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 267 | 08.08.2022 | Approving the extension of the implementation period of the project “Joint risk management and partnership in the border region Calarasi - Dobrich”, e-MS code: ROBG-415, Lead Beneficiary – Dobrichka Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 268 | 18.08.2022 | Approving the extension of the implementation period of the project “Well-developed transportation system in the Euroregion Ruse-Giurgiu for better connectivity with TEN-T network”, e-MS code: ROBG-425, Lead Beneficiary – Territorial Administrative Unit – Giurgiu Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 269 | 25.08.2022 | Approving the modifications for the project “Tourism as a bond of perspective development of border region”, e-MS code: ROBG-568, Lead Beneficiary – Dolna Mitropolia Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 270 | 20.09.2022 | Approving the extension of the implementation period for the project “A joint opened window to the universe mysteries” e-MS code: ROBG-528, Lead Beneficiary – Natural Science Museum Complex Constanta, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 271 | 17.10.2022 | Approving the modifications of the project “Better connection of Alexandria and Cherven Bryag to TEN-T”, e-MS code: ROBG-306, Lead Beneficiary – Territorial Administrative Unit – Alexandria Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 272 | 21.10.2022 | Approving accurate reporting of the project ROBG-2, contribution to the Programme result indicators values when reporting to the European Commission | Approved Written procedure | n/a |
| 273 | 21.10.2022 | Approving the extension of the implementation period for the project “Tradition and Dance – Bridge over the Danube” e-MS code: ROBG-511, Lead Beneficiary – Territorial Administrative Unit – Contesti Commune, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 274 | 07.11.2022 | Approving the extension of the implementation period for the project “Creating an innovative and integrated cross-border tourist product between "Vrachanski Balkan" and "Iron Gate" natural parks”, e-MS code: ROBG-378, Lead Beneficiary – Administration of Natural park "Vrachanski Balkan", in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 275 | 07.11.2022 | Approving the extension of the implementation period of the project “Streamlining the joint response actions to emergency situations”, e-MS code: ROBG-351, Lead Beneficiary – General Inspectorate for Emergency Situations, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 276 | 21.11.2022 | Approving the Annual Communication Plan for 2023 for Interreg V-A Romania-Bulgaria Programme | Approved MC 14 21.11.2022 Online meeting | n/a |
| 277 | 21.11.2022 | Approving the Summary of evaluation findings for Interreg V-A Romania-Bulgaria Programme | Approved MC 14 21.11.2022 Online meeting | n/a |
| 278 | 25.11.2022 | Approving the extension of the implementation period of the project “Better connected secondary and tertiary nodes to TEN-T core and comprehensive network through joint CBC measures”, e-MS code: ROBG-383, Lead Beneficiary – Veliko Tarnovo Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 279 | 28.11.2022 | Approving the extension of the implementation period, for the project “Dolj-Montana: Joint steps for a better connectivity”, project e-MS code: ROBG-375, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 280 | 13.12.2022 | Approving the modifications for the project “Restoration of Unique Common Cultural Heritage and Promotion of Joint Tourism Product “HAMANGIA - First Civilisation of Old Europe”, e-MS code: ROBG-407, Lead Beneficiary – Shabla Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 281 | 10.01.2023 | Approving the modifications for the project “The Bridges of Time& An Integrated Approach for Improving the Sustainable Use of Nikopol – Turnu Magurele Cross-border Cultural Heritage”, e-MS code: ROBG-128, Lead Beneficiary – Nikopol Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 282 | 17.01.2023 | Approving the modifications for the project “Reconstruction and display of iconic cultural sites with high tourism potential in the Euroregion Ruse-Giurgiu”, e-MS code: ROBG-424, Lead Beneficiary – Ruse Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 283 | 20.01.2023 | Approving the modifications for the project “Efficient management in emergency situations in the cross – border region Calarasi – Veliko Tarnovo”, e-MS code: ROBG-481, Lead Beneficiary – Territorial Administrative Unit – Călărași County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 284 | 23.01.2023 | Approving the extension of the implementation period for the project “Investments for a Safe Region: Giurgiu County and Ruse District – 15.3.1.023”, e-MS code: ROBG-135, Lead Beneficiary – Territorial Administrative Unit - Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 285 | 06.02.2023 | Approving the modifications for the project “Co-ordinated and efficient reactions of the authorities in the emergency situations in Dolj-Vratsa region”, e-MS code: ROBG-195, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 286 | 14.02.2023 | Approving not to recover an amount unduly paid if the amount to be recovered from the beneficiary, not including interest, does not exceed EUR 250 in contribution from the ERDF Funds to an operation in an accounting year | Approved Written procedure | n/a |
| 287 | 14.02.2023 | Approving the revised List of ceilings of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 288 | 20.02.2023 | Approving the Action Plan for Closure of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 289 | 20.02.2023 | Approving the extension of the implementation period, for the project “Dolj-Montana: Joint steps for a better connectivity”, project e-MS code: ROBG-375, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 290 | 20.02.2023 | Approving the extension of the implementation period of project “A joint opened window to the universe mysteries”, e-MS code: ROBG-528, Lead Beneficiary Natural Science Museum Complex Constanta, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 291 | 05.04.2023 | Approving the extension of the implementation period, for the project “Targeted efforts for improving road infrastructure in the cross border area”, project e-MS code: ROBG-408, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 292 | 20.04.2023 | Approving the modifications for the project “Preventing forest fire in Dolj and Lom, Montana cross border region”, e-MS code: ROBG-409, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 293 | 27.04.2023 | Approving the extension of the implementation period of the project “Development of the River Danube for better connectivity of the Euroregion Ruse-Giurgiu with Pan-European transport corridor №7” e-MS code: ROBG-130, Lead Beneficiary – Ruse Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 294 | 08.05.2023 | Approving the extension of the implementation period of the project “Joint Investments in the Field of Emergency Situations for Olt County Council and Dolna Mitropolia Municipality”, e-MS code: ROBG-244, Lead Beneficiary – Territorial Administrative Unit - Olt County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 295 | 17.05.2023 | Approving the modifications for the project “Partnerships for Overcoming the Disasters for a safe region”, e-MS code: ROBG-427, Lead Beneficiary – Territorial Administrative Unit – Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 296 | 18.05.2023 | Approving the Annual Implementation Report for 2022 of the Interreg V-A Romania-Bulgaria Programme | Approved Written procedure | n/a |
| 297 | 31.05.2023 | Approving the extension of the project implementation period of the project “A Cross Border Union in the Shadow of History”, e-MS code: ROBG-134, Lead Beneficiary – TAU Harsova Town, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 298 | 29.06.2023 | Approving the extension of the implementation period, for the project “Dolj-Montana: Joint steps for a better connectivity”, project e-MS code: ROBG-375, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 299 | 05.07.2023 | Approving accurate reporting of project RoBg-259, contribution to the Programme output indicators values when reporting to the European Commission | Approved Written procedure | n/a |
| 300 | 10.07.2023 | Approving the extension of the implementation period, for the project “Reconstruction and display of iconic cultural sites with high tourism potential in the Euroregion Ruse-Giurgiu”, project e-MS code: ROBG-424, Lead Beneficiary – Ruse Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 301 | 31.07.2023 | Approving the modifications for the project “Improving safety of navigability on Danube river in the Calarasi – Silistra cross – border region”, e-MS code: ROBG-478, Lead Beneficiary – Territorial Administrative Unit – Calarasi County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 302 | 03.08.2023 | Approving the extension of the implementation period, for the project “Targeted efforts for improving road infrastructure in the cross border area”, project e-MS code: ROBG-408, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 303 | 10.08.2023 | Approving the extension of the implementation period of the project “Developing common tourism products and rehabilitation of cultural heritage”, e-MS code: ROBG-491, Lead Beneficiary – Silistra Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 304 | 16.08.2023 | Approving the modifications for the project “Tourism as a bond of perspective development of border region”, e-MS code: ROBG-568, Lead Beneficiary - Dolna Mitropolia Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 305 | 01.09.2023 | Approving the extension of the implementation period of the project Restoration of Unique Common Cultural Heritage and Promotion of Joint Tourism Product “HAMANGIA - First Civilisation of Old Europe”, e-MS code: ROBG-407, Lead Beneficiary – Shabla Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 306 | 11.09.2023 | Approving the extension of the implementation period, for the project “Dolj-Montana: Joint steps for a better connectivity”, project e-MS code: ROBG-375, Lead Beneficiary – Territorial Administrative Unit – Dolj County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 307 | 03.10.2023 | Approving the modifications for the project “Well connected nodes Giurgiu - Borovo to TEN-T transport network”, e-MS code: ROBG-440, Lead Beneficiary – Territorial Administrative Unit - Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 308 | 20.10.2023 | Approving the extension of the implementation period of the project Efficient management in emergency situations in the cross – border region Calarasi – Veliko Tarnovo, e-MS code: ROBG-481, Lead Beneficiary – Territorial Administrative Unit – Călărași County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 309 | 20.10.2023 | Approving the extension of the implementation period for the project “Investments for a Safe Region: Giurgiu County and Ruse District – 15.3.1.023”, e-MS code: ROBG-135, Lead Beneficiary – Territorial Administrative Unit - Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 310 | 20.10.2023 | Approving the extension of the implementation period, for the project “Sustainable cross-border tourism products for Memorial Park “Grivitsa” and "Turnu" Fortress”, project e-MS code: ROBG-397, Lead Beneficiary – Pleven Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 311 | 26.10.2023 | Approving the amendment of MC Decision no. 307/03.10.2023 | Approved Written procedure | n/a |
| 312 | 06.11.2023 | Approving the extension of the implementation period of the project “Development of the River Danube for better connectivity of the Euroregion Ruse-Giurgiu with Pan-European transport corridor №7” e-MS code: ROBG-130, Lead Beneficiary – Ruse Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 313 | 13.11.2023 | Approving the lists of un-finalized and non-functional projects, financed under the Interreg V-A Romania - Bulgaria Programme | Approved Written procedure | n/a |
| 314 | 06.12.2023 | Approving the modification of the Rules of Procedures for Interreg V-A Ro-Bg Programme Monitoring Committee | Approved Written procedure | n/a |
| 315 | 18.12.2023 | Approving the modifications for the project “Well connected nodes Giurgiu - Borovo to TEN-T transport network”, e-MS code: ROBG-440, Lead Beneficiary – Territorial Administrative Unit - Giurgiu County, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |
| 316 | 20.12.2023 | Approving the modifications for the project “Better connected secondary and tertiary nodes to TEN-T core and comprehensive network through joint CBC measures”, e-MS code: ROBG-383, Lead Beneficiary – Veliko Tarnovo Municipality, in implementation under Interreg V-A Ro-Bg Programme | Approved Written procedure | n/a |