## Slide 1
Reporting
Calarasi, 18.04.2019

## Slide 2
Where? in eMS.
Notes: For INTERREG V-A Romania – Bulgaria, project reporting is made through the electronic system eMS. The Programme bodies developed an eMS reporting guide “Reporting in eMS Guidance for lead beneficiaries and partners”, available for download on eMS login page
http://ems-robg.mdrap.ro/app/main?execution=e1s1
There are 2 type of reports:
Partner report – made by each partner for his share of activities and expenditure
Project report – made by LB that aggregates information on project level.
The reporting section becomes available to project partners as soon as the project has been contracted in e-MS.
Actions to be performed in the e-MS system after signing the subsidy/co-financing contracts:
after signing the subsidy and co-financing contracts (for all beneficiaries) along with all the annexes, the Lead Beneficiary has 10 working days, starting from the date each contract was signed, in order to scan and upload the contracts in the electronic system, within the “Attachments” section from the Application.
the Lead Beneficiary has 2 working days to fill in all the requested data from the “Supplementary Information” (according to the provisions of the e-MS Guidance Reporting) section, especially the following: “Project Management”, “Bank Information”, “User Assignment”, “Physical location of the documents” and “Partnership Agreement” and upload the following:
• The scanned Financial Identification Forms for Euro account of LB where ERDF will be reimbursed by MA according to contract provisions and for Romanian partners only the Lei accounts, where prefinancing will be received, within the “Bank Information” section;
• The scanned Partnership Agreement, within the “Partnership Agreement” section.

## Slide 4
Why do we need reports?
Anytime
Every 6 months
Notes: Reporting is necessary for the beneficiaries to receive reimbursement for the expenditures they’ve already performed.
But reporting is also necessary for the Programme, we need to know how the project is going, if you are making progress towards your tarkets, if you have problems aso.
When requesting amounts for FLC verification, each partner (including LB) creates their own individual partner reports reflecting their share of activities and expenditure, according to the AF. In this respect, each partner (including LB) fills in the individual partner report, using their own e-MS account. Each partner report with expenditure is verified by the partner’s FLC in e-MS and then is included by the LB in a project report.
Partner reports with only information regarding the progress of activities (with 0 expenditure requested) are submitted by the partners directly to the LB.
Each partner should create and submit to the LP at least one such report every 6 months, according to the established schedule for reporting the consolidated progress of activities at project level. If there is no sufficient activity to report on, the partner fills-out all other parts of the report (e.g. problems and deviations, activities if any, forecast for the next report) and submits the partner report with NO expenditure declared directly to the LP.

## Slide 5
Partner report
-by each partner
Min. 5.000* euro
Project report
-by Lead Beneficiary
(aggregated for all partners)
Min. 10.000 euro
Notes: Each beneficiary that has expenditure incurred and paid for at least 5.000 Euro, can initiate a partner report in eMS and submit it in the system for FLC verification (in this case, the partner report should also contain the description of the progress of activities).
Partner reports are used for requesting validation from FLC for expenditure incurred and/or for providing information/progress of activities for project consolidated activities progress report to the LB.
Partner reports may cover only activities of individual project partners - in which case they can be submitted in e-MS directly to LB or they may contain both activities and expenditure of individual project partners which need to be verified by first level controllers (called FLC) in the system - in which case they must be submitted in e-MS to FLC.
If necessary, more than one partner report can be created for a defined period.
The information provided by each partner in their partner reports is then integrated by the LP into project report. Partner reports created by mistake should be deleted (before submitted)!

## Slide 6: Partner reports
Notes: Once the project is contracted, the overview of partner reports will automatically be displayed when a partner is accessing his project Dashboard.
If a user has multiple roles in the system (e.g. lead partner and partner at the same time), it is necessary to select the role from the dropdown menu at the top of the interface called ‘Select role’.
Please note that the lead beneficiaries must create their own partner reports as “PP”, not as “LP”. The LP role is exclusively for creating Project reports.
By default, it is possible for each partner to create one partner report per period. The creation of other (second, third) report(s) for a defined period is only possible if the LP contacts the JS officer (via e-MS message for example) and asks for JS permission, by clearly mentioning the partner and reporting period for which such a permission is requested.

## Slide 7: Project reports
eMS tutorial https://www.youtube.com/watch?v=l4y-lFHgOaI&t=5s
Notes: Project reports are created by the LB, based on partner reports: LB creates the project reports in the system and submits them to JS. The LB can access the partner reports and the FLC certificates of all partners in the e-MS to fill in the project report. LB can create a financial project report in the system requesting amounts for reimbursement from the programme no later than 3 working days from the date when FLC certificates are summing up more than 10.000 Euro (from all partners) are available in the system, even if not all partners have FLC certificates to be included in the project report.
The LB needs to also have his partner report checked by FLC controller. Financial data is automatically integrated in the project report by the e-MS. These financial project reports will be created by LB only by attaching the available FLC certificates. No other sections required by the project report template will be filled in. Project report 0 and last project report in the eMS should be consolidated (containing both certificates and activities).
eMS tutorial
It is mandatory for the LP to create a consolidated project progress report on activities in the system according to the established schedule for reporting the consolidated progress of activities at project level established within the MA Instruction no. 5 for beneficiaries for call 1-hard and call 2 projects and every 6 months for call 3 projects.
The technical project report must be submitted using the eMS system within a deadline of maximum 10 working days since the last day of the reporting period, as defined within the Annex 1 of the MA Instruction no. 5 for beneficiaries for call 1-hard and call 2 projects and after the end of every 6 months period for call 3 projects).
Such reports on the progress of activities should not include FLC certificates with amounts to be requested for reimbursement by the programme. The activities progress has to be aggregated manually by the LP (using the information provided by the partner/in the partner reports). All sections of the Project Report will be filled in by the LP in a clear and concise manner. Section “Highlight of the main achievements” includes the main achievements of the project with a focus on the content-related activities, in an understandable language even for non-specialists and in a cumulative way (providing an overview from the start of the project to the current period). The project report is submitted by LP to the JS.
Deficiencies in preparing the project report may result in clarification(s) requested by the JS and sending back the report to the beneficiaries for modifications! eMS tutorial on how to create Partner/Project reports can be found

## Slide 8
“Beginners learn the rules.
Experts know the exceptions”
Notes: For period “0” all partners must create a partner report. If no expenditures are to be claimed the partner report this should be submitted directly to LB, otherwise to FLC.
By exception, partner report 0 and final partner report may be requested for FLC verification even for lower amounts than 5.000 Euro.
In cases a partner is in danger of missing the target at half implmenentation, the respective partner may submit a partner report with a value lower than 5.000 Euro.
Preparation costs can only be requested in the first project report! Therefore even if the total amount at project level is below the 10,000 euro threshold, a project report must be created and submitted to JS.
Even the final amounts requested from the Programme are below 10.000 Euro, a project report can be created and submitted to JS. If necessary, more than one project report requesting amounts for reimbursement can be created for a defined period.

## Slide 9: Revenue generating projects
key word is net revenue
1. Projects for which it is objectively impossible to estimate the net revenue in advance
2.Projects for which the deducted discounted net revenue was initially underestimated
Notes: The following articles of EU Regulations are the legal basis to be taken into account as far as revenues are concerned:
Articles 61 to 65(8) and Annex V of Regulation (EU) No 1303/2013
Articles 15 to 19 of Delegated Regulation (EU) No 480/2014
Definition
According to paragraph 1 of Article 61 of Regulation (EU) No 1303/2013, “net revenue” means cash in-flows directly paid by users for the goods or services provided by the project, such as charges borne directly by users for the use of infrastructure, sale or rent of land or buildings, or payments for services less any operating costs and replacement costs of short-life equipment incurred during the corresponding period.
Project’s budget annexed to the Application Form shall not include the net revenue. The net revenue shall be mentioned, however, in the (full) application form.
Thus, projects generating net revenue are requested to estimate the net revenue and exclude it from the project budget at the moment of the project submission. Nevertheless, the following cases may appear:
1. Projects for which it is objectively impossible to estimate the net revenue in advance
Pursuant to paragraph 6 of Article 61 of Regulation (EU) No 1303/2013, where it is objectively not possible to estimate the revenue in advance, the net revenue generated within three years of the completion of the project or by the Programme closure deadline, whichever is earlier, must be deducted from the project’s eligible value. Projects falling into the scope of this legal provision shall self-declare the net revenue generated during the first three years after project closure or Programme closure deadline, whichever comes first. ERDF reimbursements to the Programme shall be made accordingly.
2.Projects for which the deducted discounted net revenue was initially underestimated
If the discounted net revenue deducted from the project’s budget before submitting the Application Form was underestimated, then this will have to be regularized. The additional net revenue generated during implementation of the project, resulting from sources of revenue not taken into account in determining the potential net revenue of the project, shall be deducted from the eligible expenditure of the project.

## Slide 10: Revenue generating projects are closely monitored
Notes: Art.3 Subsidy contract
3) The additional net revenue generated during implementation of the project, resulting from sources of revenue not taken into account in determining the potential net revenue of the project, shall be deducted from the eligible expenditure of the project.
4) Where it is objectively not possible to determine the revenue in advance based on the method set out in Article 61 paragraph 3(b) of Regulation 1303/2013, the net revenue generated within three years of the completion of the project, or by the deadline for the submission of documents for Programme closure, whichever is the earliest, shall be deducted from the project eligible value.
Therefore, beneficiaries need to be aware of the fact that in case of projects generating net revenue, a close monitoring will be put in place by the Programme and they will be requested to declare any additional net revenue generated, which will have to be reimbursed to the Programme.

## Slide 11: PROJECT PROCUREMENTS
Online tutorial on how to fill in this section available on Programme website:
https://www.youtube.com/watch?v=vE_Q6AiMI1o&feature=youtu.be
Notes: All partners (including LB) shall fill in here the details for their own procurements. In this section each partner will add and visualize only their own procurements with the exception of LB which can visualize all the procurements filled in the system by all partners.
The entire procurement documentation shall be uploaded in the Upload section of each procurement contract:
procurement files (tender dossier, announcement, bids from tenderers, evaluation reports, award documents, all relevant documents related to this procurement …)
services contract
addenda to the contract
in case of equipment and services procured under a works contract all the related documents will be attached.
Each procurement is available in the List of expenditure of relevant partner and can be linked to an invoice in a partner report. Once such a link is created, and you will request for FLC verification invoices related to a procurement, the list of invoices for each procurement shall be populated. This list can be exported to Excel (by pressing the “Export” button below the list).

## Slide 12
Responsible partner
Contract type
Contract no+date+name
Amount
Eligible expenditure
Type of procurement+date
Contractor Name
Succinct details
Problems?
Notes: The following information is mandatory to be fill in procurement section:
Partner responsible for the procurement
Contract type (services/supplies/works)
Contract Number/Contract date; Contract Name
Contract Amount (in Euro)
Eligible expenditure incurred and paid based on contract – when the information is available at partner level
Type of Procurement Procedure Used; Date of launching in National Electronic Procurement System
Contractor Name; Unique Identifier of the Contractor
Please provide short details about the progress of the procurement
If applicable, please describe and justify any problems and deviations including delays from the work plan presented in the Application Form and solution found (e.g. details on re-launching the procedure)

## Slide 13: PUBLIC PROCUREMENTS
Fill it in any time.
You have to record ALL procurements.
You did not create procurements? No linked invoices for FLC
=> no money (FLC will revert the report)
4. Upload documents only once.
5. Link invoices and payments to the respective procurements.
6.Deliverables are uploaded separately.
Notes: The Project Procurements section can be filled in at any time during project implementation, so you can fill in procurement details just before you request in the system the first related expenditure.
Recording all the procurements of the project is compulsory!
In case you don’t create procurements in this section, you won’t be able to link the invoice to the procurement when you request it for FLC verification and your FLC request (partner report) shall be reverted!
The documents related to a procurement shall be uploaded only once in this section. The invoices and payment documents will be linked to the respective procurement (via list of expenditure of the partner report. The deliverables shall be uploaded separately in the partner report deliverable attachment section located in the reporting per work packages section and the accounting documents in the partner report attachment section.

## Slide 14: SPENDING FORECAST
www.iterregrobg.eu
Notes: In the section Contribution and Forecast of the partner report must fill in forecast spending for the following partner reports of all the periods defined in AF. The system also displays planned budget and actual spending per period.
In the Follow up section the Partner Contribution amount is split automatically by the system!

## Slide 15: Indicators
Each partner reports their contribution to the output indicators in their partner report.
LB consolidates the info in the project report.
Result indicators? Final report.
Verifiable data!
Notes: Information on specific outputs (report the progress in the output indicators), pressing the “Add Output” button and selecting each applicable output from the drop-down list with all outputs included in the AF. Also, beneficiary is asked to provide information on the target groups reached.
All indicators shall be supported by verifiable data. The justification documents attesting the reported contribution to the output indicators should be uploaded in the dedicated field “Attachment” within section “Project Main Outputs” (rather than in section “Attachments” of the Partner or Project report).
Output Indicators shall be reported by each partner in their partner reports and consolidated by LB in the project reports. Result indicators will be reported in the last / final report.

## Slide 16
3rd call was a targeted call
What happens in case you do not reach the indicators as promised in the application form by the date the AF mentioned you will*?
  Less than 75% - 10% penalty
  Less than 50% - 25% penalty
  Did not reach the result indicator (non-quantifiable)? – 10% penalty
1st plus 2nd call – procedure to be approved by MC (keep an eye on the website for updated)
Monitoring indicators
Notes: 10% decommitment will apply to the budget of the beneficiaries in case the project indicators were reached lower than 75% of the initial project indicators (average at project level considering all indicators)
25% decommitment will apply to the budget of the beneficiaries in case the project indicators were reached lower than 50% of the initial project indicators (average at project level, considering all indicators)
In case the project did not contribute to the result indicators (a non-quantifiable one) a 10% decommitment will apply to the budget of the beneficiaries.
The moment when the abovementioned is judged is represented by the deadline of achieving the indicators, as mentioned in the Application Form / the deadlines mentioned in the European Commission guidance for closure (not published yet for the current period).
If not explicitly mentioned within the AF, final date of the implementation period will be considered deadline for the realization of the outputs and results.
The target values are those established within the approved application form. Recommendations are being made to double-check the application form for any errors or miscorrelation between the activities and the proposed targets of the activities.

## Slide 17: Recommendations
Start looking at indicators as soon as you sign the contract
Always remember the baseline
Use reliable data
Underline YOUR project contribution
Sustainability
Notes: Target values and deadline for the achievement of indicators set in the AF shall be analyzed even since the very beginning of the project if feasible after implementation of the activities;
When reporting, the results shall be compared with the baseline;
Methodologies for counting the indicators shall be clear and based on reliable sources (for ex., lists of participants for people participating in initiatives, events, written agreements for number of partnerships, visit reports for increase of the number of visits, independent traffic monitor for counting the accesses on the website, etc.);
Direct impact of the projects shall be underlined (especially for indicators that are reported using statistical data or for qualitative indicators);
Sustainability shall be ensured also for the indicators, strategies and studies shall be materialized in follow up and sustainability actions.

## Slide 18: Reading is cool
Financing contracts
Project Implementation Manual
eMS Manual
All on our webiste: www.interregrobg.eu