## Slide 1
eMS Reporting - Frequent errors
Călărași, 18.04.2019

## Slide 2
Frequent errors in reporting

## Slide 3: NOT respecting the following rules
uploading the contracts in the electronic system, within
the “Attachments” section of the project after
signing the subsidy and co-financing contracts in
10 working days
filling in all the requested data from the “Supplementary
Information” section, after signing the subsidy and co-financing
contracts in 2 working days and uploading the following:
a. The scanned Financial Identification Forms for Euro account of LB and for Romanian partners only the Lei accounts;
b. The scanned Partnership Agreement.
3. Uploading the contract addenda together with the annexes in 3 working days in section “Attachments” of the project
Notes: Please note that after signing the subsidy and co-financing contracts (for all beneficiaries) along with all the annexes, the Lead Beneficiary has 10 working days, starting from the date each contract was signed, in order to scan and upload the contracts in the electronic system, within the “Attachments” section from the Application.
Also, following the signing of the subsidy contract, the Lead Beneficiary has 2 working days to fill in all the requested data from the “Supplementary Information” section (especially the following: “Project Management”, “Bank Information”, “User Assignment”, “Partner Nuts code and Project Dimensions” – as approved in MC Decision, “Physical location of the documents”, “Partnership Agreement” and “Project Procurements, for the last section from the moment when it becomes fully functional and upload the following:
a. The scanned Financial Identification Forms for Euro account of LB where ERDF will be reimbursed by MA according to contract provisions and for Romanian partners only the Lei accounts, where prefinancing will be received, within the “Bank Information” section;
b. The scanned Partnership Agreement, within the “Partnership Agreement” section.
3. The maximum size of an attachment is 50 Mb per file/package! In case the attachment/evidence exceeds the limit of 50Mb, the partners should create .rar or .zip packages of no more than 50 Mb and upload them in more parts (adding a description is necessary).
Before uploading any file in the system make sure the name of the file does not exceed 50 characters
All information to be provided by the partners as attachments to partner/project reports (e.g. invoices, procurement documents) must be scanned preferably in black and white colors and at a resolution of 300 dpi.
When you have to upload a document, a button ‘Upload’ is available to you in the system. When you click it, the upload pop up will appear and you can select one or more files (ctrl + select). The user has the option to add a description of each file or .zip /.rar packages (in English in accordance with the relevant content of documents) by clicking on the “Comment” icon.
Please coordinate with the LP to make sure that you don’t duplicate relevant evidence/attachments in the system. If the evidence/attachment was already provided in a previous Partner Report, just mention where the evidence can be found in the system (e.g. “Partner report x.1, List of expenditure – item xx”) and don’t attach it again!

## Slide 4
The maximum size of an attachment is 50 Mb per file/package!
Adding a correct description to each uploaded file, is mandatory.
5. before submitting the first project report, each Romanian beneficiary may send to the MA an advance request in original, for maximum 60% of the value of its co-financing contract, except for those beneficiaries which sign a Monitoring Agreement.
6. similarly, each Bulgarian beneficiary may send to the NA request for an advance payment in original, of maximum 80% of the value of its co-financing contract.
Notes: After the co-financing contract is signed, but before submitting the first project report, each Romanian beneficiary may send to the MA an advance request for maximum 60% of the value of its co-financing contract, except for those beneficiaries which sign a Monitoring Agreement. This request will be submitted in original and shall stipulate the percentage, the amount and the bank account where the funds should be transferred – according to financial identification annex uploaded in the section “Supplementary Information”/ “Bank Information”
Similarly, each Bulgarian beneficiary may send to the NA request for an advance payment of maximum 80% of the value of its co-financing contract. This request will be submitted in original and shall stipulate the percent and financial identification form with actual bank account
For Bulgarian co-financing contracts, please consult Annex - Co-financing package – for Bulgarian beneficiaries, attached to PIM.

## Slide 5: Extracts from eMS reports
Notes: Please note that in order to be identified and easily verified in eMS, beneficiaries must create separate archived (.zip or .rar) before uploading for each category of expenditure (e.g. one archived for Travel and accommodation, one for External expertise and services, one for Equipment expenditure and one for Infrastructure and works).
The files attached to these archives will be named in English in accordance with the relevant content of documents (e.g: agenda of the seminar/event/conference held at/on …)
Also, in the comment section, the beneficiaries must specify the budget line to which the archive is linked to.
In case the supporting documents are not properly named and/or uploaded without being linked to the corresponding budget line, the FLC controller may return the whole report to the partner for revision.

## Slide 6
2. Not filling in all mandatory fields in the List of expenditures

## Slide 7: Supporting document without stamp as required

## Slide 8: Supporting documents (invoice) stamped accordingly

## Slide 9: For 3rd call projects, IT IS A MUST to FILL IN ALL PUBLIC PROCUREMENTS and to LINK the invoices in LOE, otherwise the reports should be reverted by FLC

## Slide 10: Other issues
Not attaching in the eMS supporting documents for requested expenditures;
Not filling in the forecast for each partner report,
Not naming the files at all;
Attaching the documents without project stamp
Notes: (Please refer to Project Implementation Manual for guidance regarding stamping the supporting documents with: Programme name, project code, number of FLC request and requested amount in the currency of the invoice (only for financial documents).