## Slide 1
CONTRACT MODIFICATION
www.interregrobg.eu

## Slide 2: Contract modifications chapter 16 from the PIM
  Considering that the initial Application Form has been evaluated and selected by the Monitoring Committee it is strongly advised that partners limit the number of changes of a project.

## Slide 3: Contract modifications
  Changes which do not require the signing of an addendum to the subsidy contract – Notifications (Subsidy contract art. 13 para. 7)
  Changes which require the signing of an addendum to the subsidy contract (Subsidy contract art. 13 para. 4)

## Slide 4: Contract modifications
  Notification = minor changes which do not alter in a significant way the approved Application Form.
  The JS will analyse the request in order to verify if it does not fall under one of the cases for which an addendum to the subsidy contract needs to be signed.

## Slide 5: Contract modifications Notifications
  Examples
  contact data change;
  change of the bank account of the LB;
  modification of the name of the beneficiary (without changing the identification number of the institution);
  minor changes in the application form;
  material errors in the text of the contract.

## Slide 6: Contract modifications Addenda
  Changes which have a major impact on the approved Application Form shall require the signing of addendum to the contract.
  Beneficiaries should try to limit these changes as much as possible, as they usually alter the initial financing conditions.

## Slide 7: Contract modifications
  Addenda
  Examples
  major changes in the Application Form;
  changes in the project partner organizations (name, headquarter, etc.);
  changes in the partnership (requires MC approval);
  Extension of the implementation period (requires MC approval);
  reallocation of funds between budgetary chapters (only in exceptional and duly justified cases).

## Slide 8
  A request for modification should be submitted to the JS with minimum 30 days before they intend to produce effects.
  The last request for modification should be submitted no later than 2 months before the end date of the implementation period.
  The requests for modification have to be submitted by the LB to the JS. Therefore, take also into consideration the time necessary for the LB to compile the requests for modification received from the project partners.

## Slide 9
  The request for modification has to be based on the latest approved application form and needs to be updated for the respective parts related to the change.
  Please note that in case a partner report is submitted to FLC while a modification request is pending, the first level controllers will analyse if the modification request is linked to the expenditures submitted for control. If so, the partner report will be reverted to the beneficiary, in order to exclude the expenditures affected by the modifications from the report and reintroduce them after the modification request is approved, in another report.

## Slide 10: Workflow
  The LB will initiate the modification request in the eMS system, as foreseen within the eMS guidance, submitting also an e-mail in the eMS system to the designated JS officers (the entire procedure is available in the Project Implementation Manual, chapter 16).
  The JS analyses the proposal in 20 working days. Additional information/document/clarifications may be requested (the deadline for analysis is suspended in this case).

## Slide 11
The content of this material does not necessarily represent the official position of the European Union
www.interregrobg.eu
Workflow
  In case of addendum, LB submits the addenda (signed, stamped and dated) by post / courier / directly to MA. MA may request clarifications / modification of the already submitted documents to LB, if the case.
  After the MA (MRDPA) representative signs the addenda and the documents are received by JS, the latter will submit the addenda (including annexes) to the beneficiaries by post / courier.
  After receiving the addenda, LB must upload the signed addenda and the annexes in eMS, section “attachments” in maximum 3 working days.
Thank you for your attention