## Slide 1
Most Common Errors
in Project Reporting
6th July 2020, Slatina, Romania
7th July 2020, Ruse, Bulgaria

## Slide 2
Common Errors
in Partner Reports
The justification documents uploaded are named in RO or BG language, rather than EN, as required by the Programme; the name of the document does not reflect its content; or the file is not named at all;

## Slide 3
Common Errors
in Partner Reports
The partners do not describe their individual contribution to the Project output indicators;
The partners do not describe their individual contribution to reaching the target groups;

## Slide 4
Common Errors
in Partner Reports
when reporting progress per WPs/Activities:
the progress in activities during the reporting period, which is not yet paid for, is not reported;
very general terms used when describing the progress of activities - what, by whom, when, purpose and effect/result;
focus on documentary evidence when describing the progress of activities - actual output, content, scope or objective of the activity;
No explanations/solutions/measures for registered delays in activities

## Slide 5: Common Errors in Partner Reports
when reporting progress per Deliverables
  No deliverables/deliverable evidence are provided
  The description of the progress in the deliverable repeats the information provided for the progress in the activity
  “Deliverable description” indicates the documents, uploaded as deliverable evidence – specific equipment delivered or services provided

## Slide 6
Common Errors
in Technical Project Reports
The reporting period of the project report is not entirely covered by partner reports from all beneficiaries;
The progress reported in the partner reports is not entirely consolidated at project level in the technical project report
When consolidating the physical progress of the project, described by the partners in their individual partner reports, the LB copies the information provided mechanically, thus describing the progress per partners and sub periods, which results in discrepancies, duplicating of information, and generally incoherent and difficult to comprehend picture of the project physical progress;
Not all fields of the project report are filled in;
“Highlights of Main Achievements” LB consolidates the information provided in project summary in each partner report for the period – focus on the major outputs/achievements

## Slide 7
Common Errors
in Technical Project Reports
Double-counting of people, when reporting target groups reached or project indicators – one person, who has taken part in 2 events/actions is reported as 2 persons
The reported contribution to the Output indicators is not supported by evidence, uploaded in the dedicated field “Project Main Outputs” -> “Attachments”, and relevant description in the individual partner reports.

## Slide 8
Common Errors
in Technical Project Reports
Target Groups reached:
The target groups reached are not reported at all, or, if reported, they are not split per categories
the field “Description of target group” is filled in with the name of the target group category or some general reference;
no verification sources are provided or indicated in the dedicated category;
project management team members or other partner representatives taking part in project events are reported among the target groups reached or as a contribution to the project indicators

## Slide 9
Common Errors
in Final Reports
The progress described in the last project report in e-MS covers the entire project implementation, rather than the last 6-month period
The Final Implementation Report is not submitted together with the last project report with expenditure;
The information provided per activities in the Final Implementation Report just consolidates the information reported per activities in the intermediary project reports - main outputs and results, their further use and contribution to the project implementation
The Final Implementation Report does not cover the entire period of the project implementation;
List of participants in trainings is not submitted with the Final Implementation Report, when the project included trainings.